## Work Calendar
	Monday	Tuesday	Wednesday	Thursday	Friday	Notes
	9/7	9/8	9/9	9/10	9/11
Morning		Clarence
		Howard
		Steve

Afternoon					Everardo

	8/31	9/1	9/2	9/3	9/4
Morning	Clarence
	Howard
	Steve
	Anne
Afternoon

	8/24	8/25	8/26	8/27	8/28
Morning	Anne	POWER OUT			Steve
	Howard				Howard
	Steve				Joe
	Joe H
Afternoon					elevator maintenance

	8/17	8/18	8/19	8/20	8/21
Morning		Clarence			Howard
		Howard			Anne

Afternoon					Oscar

	8/10	8/11	8/12	8/13	8/14
Morning		Howard Budd	Howard Budd		Howard Budd	Clarence isolating
		Joe Harris				Anne isolating

Afternoon	Steve Hahn	Howard Budd	Howard Budd		Oscar
	Joe Harris	Joe Harris			Everardo

	8/3	8/4	8/5	8/6	8/7
Morning	Joe Harris	Howard Budd			Howard Budd	Clarence isolating
	Howard Budd	Steve			Steve	Anne isolating

Afternoon	Joe Harris	Howard Budd			Oscar
	Howard Budd	Steve			Everardo

	7/26	7/27	7/28	7/29	7/30
Morning	Howard	Howard			Joe H	Clarence isolating
	Steve	Steve			Andrew	Anne isolating

Afternoon		Everardo
		Zubair						BEFORE FNAL COVID CLOSURE

	7/20	7/21	7/22	7/23	7/24				Monday	Tuesday	Wednesday	Thursday	Friday	Notes
Morning			Anne		Clarence (all day)	Howard ICARUS Tuesday, Wedneday, Friday			2/3	2/4	2/5	2/6	2/7
			Zubair		Howard (all day)			Morning		No Shifts				Joe on holiday all week
			Everardo								Howard in Penn
			Joe
Afternoon			Steve		Oscar (afternoon)			Afternoon

									2/10	2/11	2/12	2/13	2/14
	7/13	7/14	7/15	7/16	7/17			Morning					Zubair	Skippy at ICARUS all week
Morning		Anne (all day)	Anne (all day)		Joe (all day)	First week of MINERvA students					Anne gone 2/12-2/19
		Clarence (all day)	Clarence (all day)		Skippy (all day)						Howard in Penn until 2/17
		Joe (all day)	Joe (all day)		Howard (all day)			Afternoon
		Skippy (all day)	Howard (all day)		Steve (all day)						MINOS work until Thursday
Afternoon		Howard (all day)			Oscar (afternoon)
			Zubair(AfterNoon)		Everardo (afternoon)				2/17	2/18	2/19	2/20	2/21
					Zubair (AfterNoon)			Morning		No Shifts / (Waiting for plane removal / and alignment)				Howard back 2/17
											Anne back 2/20
	7/6	7/7	7/8	7/9	7/10
Morning		Joe	Joe (all day)	Steve		Skippy doing HV at ICARUS		Afternoon
		Howard	Anne (morning)	Howard		MINERvA week, no MINERvA students
		Steve	Steve (all day)	Joe		Clarence car fails...
		Anne	Clarence (all day)	Anne					2/24	2/25	2/26	2/27	2/28
Afternoon			Howard (afternoon)					Morning		No shifts / (plane removal)

								Afternoon
	6/29	6/30	7/1	7/2	7/3
Morning						Entire week cancelled due to elevator problems
									3/2	3/3	3/4	3/5	3/6
								Morning	No shifts / (Water target measurements)				Aaron
											Zubair
Afternoon											Diego
								Afternoon

	6/22	6/23	6/24	6/25	6/26				3/9	3/10	3/11	3/12	3/13
Morning				Clarence		Elevator Friday		Morning	Javier			Javier	Diego/Oscar
				Anne		All week slow plane moving			Oscar			Oscar	Zubair/Javier
				Steve					Everardo			Everardo	Aaron/Everardo
				Howard				Afternoon
Afternoon

									3/16	3/17	3/18	3/19	3/20
								Morning	Javier	Diego		Javier	Diego
	6/15	6/16	6/17	6/18	6/19				Oscar	Aaron		Oscar
Morning	Steve		Steve		Steve				Everardo			Everardo
	Anne				Anne			Afternoon
	Clarence				Clarence
	Howard				Howard
Afternoon

## Work sheet
Monday	Tuesday	Wednesday	Thursday	Friday
9/7	9/8	9/9	9/10	9/11
No shifts / (Labour Day)	MS24 FEB	No shifts
	Lab 8 move

8/31	9/1	9/2	9/3	9/4
MS21 cables	MS22 finish	No shifts	No shifts	MS23 finish
MS22 PMT	MS23 FEB/PMT

8/24	8/25	8/26	8/27	8/28
MS19 cables		No shifts	No shifts	MS20 finish
				MS21 FEB/PMT
				NO AFT SHIFT
8/17	8/18	8/19	8/20	8/21
	MS19 FEB/PMT	No shifts	No shifts

8/10	8/11	8/12	8/13	8/14
	MS17	No shifts	No shifts
				MS18

8/3	8/4	8/5	8/6	8/7
MS15	MS16	No shifts	No shifts	MS16

7/27	7/28	7/29	7/30	7/31
MS14 / cables	MS14 / cables	No shifts	No shifts

7/20	7/21	7/22	7/23	7/24
No shifts	No shifts	MS12 PMT / cables / MS13 FEB	No shifts	MS13 PMTs / Cables

				MS14 FEBs
7/13	7/14	7/15	7/16	7/17
No shifts	MS10 / PMT / FEB / Cables	MS11 / PMT / FEB / cables	No shifts	MS12 / FEB

7/6	7/7	7/8	7/9	7/10
No shifts	MS8 / PMT FEB	MS8 cables, / MS9 PMT FEB	MS9 / PMT / FEB	MS9 / cables

6/29	6/30	7/1	7/2	7/3
No shifts / (elevator maintenance)

6/22	6/23	6/24	6/25	6/26					2/3	2/4	2/5	2/6	2/7
No shifts / (Plane removal)			MS7 / PMT FEB	No shifts / (elevator / maint.)					MS2 / fibre optics	No shifts

6/15	6/16	6/17	6/18	6/19					2/10	2/11	2/12	2/13	2/14
Inspection / (HA drafting)	No shifts	MS6 / PMT, FEB	No shifts	MS6 / cables					MINOS work				MS2 / PMT, FEB

									2/17	2/18	2/19	2/20	2/21
									MS2 / cables	No shifts (plane rem., / alignment water target)

									2/24	2/25	2/26	2/27	2/28
									All FESB / removal / Pull back / veto cables	No shifts / (plane removal)

									3/2	3/3	3/4	3/5	3/6
									No shifts / (Water target measurement)				MS3 fully / disassembled

									3/9	3/10	3/11	3/12	3/13
									MS4 / cable check	MS4 fully / disassembled	No shifts / (Plane removal, YouTube video)

									3/16	3/17	3/18	3/19	3/20
									No shifts / (plane / removal)	MS5 / cable check	No shifts / (plane removal)		COVID-19 / closure
									MS5 fully / disassembled

									3/23	...	...	...	6/12
									Long COVID-19 closure

## Signup sheet
End of January - Mid April 2020
Name (Affiliation)	Aerial Lift training?	Underground training?	Definitely available	Probably available	Absolutely not available	Weekly commitments
Clarence (Rochester)	OK	OK	End of January - Mid March		1-9 May 2020	Chairing meetings Monday, Tuesday, Thursday, Friday mornings every two weeks or so
Anne (FNAL)	1a 1c OK, no boom	OK			Jan 23, Feb 12-20, NOvA Meeting	Meeting every other Thursday
Adi (MIT)	Need	OK		January 10th - End of February	untill January 8th	Chairing meetings Wednesday's morning
Dan (MSU)	Need	OK			Jan 25 - Feb 2, DUNE Meeting	Meeting 12:30 every other Thursday, 11:00 the other "every other Thursday"
Howard (Rochester)	OK	OK
Steve (FNAL)	OK	OK	Mostly available, some MAGIS-100 commitments			MAGIS meetings: Tues 1:00 PM, Wed 1:00 PM, occasional one-offs
Joe Brown (Skip) (FNAL, Linda tech)	OK	OK
Joe Harris (FNAL, Linda tech)	OK	OK
Andrew Olivier (Rochester)	Need	OK	All of January - February 25 / March 2-6, March 18 - finished	March 7 - March 17	February 25-28	Class Mondays and Wednesdays from 11-1, Monday afternoons, Tuesday mornings, Thursday mornings, Friday afternoons
Francisco Javier Rosas Torres (Guanajuato)	Need	OK	End of January - February	March	Feb 12 , Feb 27-29	Mondays, Tuesdays and Wednesdays from 8-12
Oscar Moreno-Palacios (Guanajuato)	Need	OK	February - First days of March		2 March	Mondays, Thursdays any time. Tuesdays and Fridays 8-12 hrs. Wednesdays not available.
Everardo Granados Vazquez (Guanajuato)	Need	OK
Zubair	Need	OK	Most of the time			Meeting on Tuesday 11-12 am, Wednesday 9:30 am - 2pm
Diego Andrade (Guanajuato)	Need	OK	Left USA	Thursdays	Tuesdays and Wednesdays	Meetings on Tuesdays and Wednesdays, Fridays at noon and Thursdays at 2 pm
Huma	Need	Need	Left USA
Aaron Bercellie	Need	OK

Unsure
Kami (W&M, Jeff Nelson tech)
Will (W&M, Jeff Nelson shop foreman)
David Last (Penn)
Drew (FNAL, Aria Soha mech tech)

Useful links/talks				Possible clashes
Webcam (only viewable on FNAL IP)	minervacam.fnal.gov
Instructions	http://www.pas.rochester.edu/~cwret/minerva_decom/Instructions_Slides.pdf
	http://www.pas.rochester.edu/~cwret/minerva_decom/Instructions_Hazard.pdf
FEB/PMT number table	https://docs.google.com/spreadsheets/d/1zvW4zTIZz7u11L01bU8YaNx8mrlkM_IK5XwGg8iB0e8/edit#gid=0
Ting, Dec ArgonCube CM	https://indico.fnal.gov/event/20432/session/15/contribution/34/material/slides/0.pdf

## Contact details
Name	Email	Phone
Clarence (Rochester)	c.wret@rochester.edu	331-234-1666
Anne (FNAL)	norrick@fnal.gov	763-350-7769
Adi (MIT)	adishka@gmail.com
Dan (MSU)	dougl215@msu.edu
Howard (Rochester)	hbudd@fnal.gov	814-810-8591
Steve (FNAL)	hahn@fnal.gov
Joe Brown (Skip) (FNAL, Linda tech)	skipman@fnal.gov
Joe Harris (FNAL, Linda tech)	harrisj@fnal.gov
Andrew Olivier (Rochester)	aolivier@ur.rochester.edu
Francisco Javier Rosas Torres (Guanajuato)	rosastf2012@licifug.ugto.mx
Oscar Moreno-Palacios (Guanajuato)	morenopo2012@licifug.ugto.mx	477-333-3047
Everardo Granados Vazquez (Guanajuato)	granadosve2012@licifug.ugto.mx
Zubair	zubairnazir4766@gmail.com

Unsure
Drew (FNAL, Aria Soha mech tech)
David Last (Penn)	dlast@sas.upenn.edu
Kami (W&M, Jeff Nelson tech)
Will (W&M, Jeff Nelson shop foreman)

## Orders
Item	Comment	Size	Link
FEB boxes
Single padded FEB box	Fits one FEB	8x8x2 3/4"	https://www.uline.com/BL_2351/Anti-Static-Foam-Shippers?keywords=foam+boxes
Multiple padded FEB box	Fits 12 FEBs (same as above but bigger)	22x18x2 3/4"	https://www.uline.com/BL_2351/Anti-Static-Foam-Shippers?keywords=foam+boxes
Large box to put FEB boxes in	Fits 20 small FEB boxes	24x18x12	https://www.uline.com/Product/Detail/S-4219/Corrugated-Boxes-200-Test/24-x-18-x-12-Corrugated-Boxes

PMT boxes
Corrugated box for PMT storage	Fits four PMTs (too heavy to carry more than four)	18x18x6	https://www.uline.com/Product/Detail/S-4219/Corrugated-Boxes-200-Test/24-x-18-x-12-Corrugated-Boxes

Cable tray boxes
	Cable tray is 6' 8" (80"), and there are two per module set	80"	Can't find on uline

Kapton tape			FNAL stock room, $40 per roll
Sharpies			FNAL stock room/WH12
Bubble wrap			FNAL stock room